## Sheet1
	ODF 1.4 editing progress sheet

						Master documents:	Part 1	Part 2	Part 3	Part 4	Schema

				Technical / Editorial / (T/E)	Master document manual change reqd	Schema change required	Resolution text drafted		Resolution text approved by TC	Changes made to the schema		Changes made to master document		Change / recorded in / Appendix	Document for TC review created			Changes approved by TC	Further revision required
Number	JIRA/Github issue	Status in JIRA	ODF Part				Date	Initials	Link to minutes	Date	Initials	Date	Initials	Y/N	Date	Initials	Link to document	Link to minutes	Y/N

OFFICE-1909	OFFICE-1909	Applied	3	T	N	Y	2022-03-15	PD		2023-01-31	FC			Y
OFFICE-2164	OFFICE-2164	Applied	4	T	Y	N	2022-03-16	FC				2022-03-16	FC	Y
OFFICE-2390	OFFICE-2390	Applied	3	T	Y	N	2022-03-15	PD				2022-03-15	PD	Y
OFFICE-2949	OFFICE-2949	Applied	3	T	Y	N	2022-03-15	PD				2022-03-15	PD	Y
OFFICE-3005	OFFICE-3005	Applied	3	T	Y	N	2022-03-15	PD				2022-03-15	PD	Y
OFFICE-3022	OFFICE-3022	Applied	3	T	N	Y	2022-03-15	PD		2023-01-31	FC			Y
OFFICE-3685	OFFICE-3685	Applied	3	T	Y	N	2022-03-15	PD				2022-03-15	PD	Y
OFFICE-3710	OFFICE-3710	Applied	3	T	Y	N	2022-03-15	PD				2022-03-15	PD	Y
OFFICE-3741	OFFICE-3741	Applied	3	T	Y	Y	2022-03-20	PD		2023-01-31	FC	2022-03-20	PD	Y
OFFICE-3750	OFFICE-3750	Applied	3	T	Y	N	2023-01-13	PD				2023-01-13	PD	Y
OFFICE-3751	OFFICE-3751	Applied	3	T	Y	Y	2022-03-20	PD		2023-01-31	FC	2022-03-20	PD	Y
OFFICE-3759	OFFICE-3759	Applied	3	T	Y	Y	2022-03-21	PD		2023-01-31	FC	2022-11-11	PD	Y
OFFICE-3761	OFFICE-3761	Applied	3	T	N	Y	2022-03-27	PD		2023-01-31	FC			Y
OFFICE-3816	OFFICE-3816	Applied	3	T	Y	N	2022-03-27	PD				2022-03-27	PD	Y
OFFICE-3824	OFFICE-3824	Applied	3	T	Y	N	2022-03-20	PD				2022-03-20	PD	Y
OFFICE-3846	OFFICE-3846	Applied	3	T	Y	Y	2022-03-27	PD		2023-01-31	FC	2022-11-17	PD	Y
OFFICE-3851	OFFICE-3851	Applied	4	T	Y	N	2021-12-06	FC				2021-12-06	FC	Y
OFFICE-3915	OFFICE-3915	Applied	4	T	Y	N	2023-04-27	FC				2023-04-27	FC	Y
OFFICE-3936	OFFICE-3936	Applied	3	T	Y	Y	2022-03-27	PD		2023-01-31	FC	2022-11-17	PD	Y
OFFICE-3953	OFFICE-3953	Applied	3	T	N	Y	2022-03-27	PD		2023-01-31	FC			Y
OFFICE-3997	OFFICE-3997	Applied	3	T	Y	N	2022-03-27	PD				2022-03-27	PD	Y
OFFICE-4001	OFFICE-4001	Applied	4	T	Y	N	2021-12-06	FC				2023-04-24	FC	Y
OFFICE-4004	OFFICE-4004	Applied	3	T	Y	N	2022-03-27	PD				2023-03-27	PD	Y
OFFICE-4022	OFFICE-4022	Applied	3	T	Y	N	2022-03-28	PD				2022-03-28	PD	Y
OFFICE-4023	OFFICE-4023	Applied	3	T	Y	N	2022-03-27	PD				2022-03-27	PD	Y
OFFICE-4025	OFFICE-4025	Applied	3	T	Y	N	2022-03-27	PD				2022-03-27	PD	Y
OFFICE-4026	OFFICE-4026	Applied	3	T	Y	N	2022-03-27	PD				2022-03-27	PD	Y
OFFICE-4027	OFFICE-4027	Applied	3	T	Y	N	2022-03-28	PD				2022-03-28	PD	Y
OFFICE-4029	OFFICE-4029	Applied	3	T	Y	N	2022-03-28	PD				2022-03-28	PD	Y
OFFICE-4030	OFFICE-4030	Applied	3	T	Y	N	2023-08-21	FC				2023-06-22	PD	Y
OFFICE-4033	OFFICE-4033	Applied	3	T	Y	N	2022-04-20	PD				2022-04-20	PD	Y
OFFICE-4035	OFFICE-4035	Applied		T	N	Y	2022-04-20	PD		2023-01-31	PD
OFFICE-4047	OFFICE-4047	Applied	3	T	Y	Y	2022-04-20	PD		2023-01-31	PD	2022-11-17	PD	Y
OFFICE-4072	OFFICE-4072	Applied	3	T	Y	Y	2022-04-20	PD		2023-01-31	PD	2023-04-28	PD	Y
OFFICE-4073	OFFICE-4073	Applied	3	T	Y	Y	2022-04-20	PD		2023-01-31	PD	2022-04-20	PD	Y
OFFICE-4080	OFFICE-4080	Resolved	HTML artifacts?	E	N	N
OFFICE-4086	OFFICE-4086	Applied	3	T	Y	N	2022-04-21	PD				2022-04-21	PD	Y
OFFICE-4088	OFFICE-4088	Applied	2	T	Y	N	2022-04-21	PD				2022-10-01	FC	Y
OFFICE-4092	OFFICE-4092	Applied	3	T	Y	N	2022-04-21	PD				2022-04-21	PD	Y
OFFICE-4093	OFFICE-4093	Applied	3	T	Y	N	2022-04-21	PD				2022-04-21	PD	Y
OFFICE-4094	OFFICE-4094	Applied	4	T	Y	N	2021-12-06	FC				2021-12-06	FC	Y
OFFICE-4096	OFFICE-4096	Applied	4	T	Y	N	2021-12-06	FC				2021-12-06	FC	Y
OFFICE-4101	OFFICE-4101	Applied	3	T	Y	N	2022-04-21	PD				2022-04-21	PD	Y
OFFICE-4102	OFFICE-4102	Applied	3	T	Y	N	2022-04-21	PD				2022-04-21	PD	Y
OFFICE-4103	OFFICE-4103	Applied	3	T	Y	N	2022-04-21	PD				2022-04-21	PD	Y
OFFICE-4104	OFFICE-4104	Applied	3	T	Y	N	2022-04-21	PD				2022-04-21	PD	Y
OFFICE-4105	OFFICE-4105	Applied	3	T	Y	N	2022-04-21	PD				2022-11-17	PD	Y
OFFICE-4106	OFFICE-4106	Applied	3	T	Y	Y	2022-04-22	PD		2023-01-31	PD	2022-04-22	PD	Y
OFFICE-4107	OFFICE-4107	Applied	3	T	Y	Y	2022-04-22	PD		2023-01-31	PD	2022-04-22	PD	Y
OFFICE-4108	OFFICE-4108	Applied	3	T	Y	Y	2022-04-23	PD		2023-01-31	PD	2022-11-16	PD	Y
OFFICE-4110	OFFICE-4110	Applied	3	T	Y	Y	2023-01-28	PD		2023-05-02	FC	2023-01-28	PD	Y
OFFICE-4113	OFFICE-4113	Applied	4	T	Y	N	2022-09-12	FC				2023-01-31	FC	Y
OFFICE-4114	OFFICE-4114	Applied	4	E	Y	N					2023-01-31	FC	Y
OFFICE-4118	OFFICE-4118	Applied	3	T	N	Y	2022-04-22	PD		2023-01-31	PD			Y
OFFICE-4119	OFFICE-4119	Applied	3	T	Y	N	2022-04-22	PD				2023-01-22	PD	Y
OFFICE-4120	OFFICE-4120	Applied	3	T	Y	N	2023-04-24	FC				2023-01-22	PD	Y
OFFICE-4121	OFFICE-4121	Applied	3	T	Y	Y	2022-04-22	PD		2023-01-31	PD	2022-11-17	PD	Y
OFFICE-4122	OFFICE-4122	Applied	3	T	Y	Y	2022-04-22	PD		2023-01-31	PD	2022-11-11	PD	Y
OFFICE-4123	OFFICE-4123	Applied	3	T	Y	Y	2023-04-24	FC		2023-01-31	PD	2023-01-22	PD	Y
OFFICE-4125	OFFICE-4125	Applied	3	T	Y	Y	2022-11-12	FC		2023-01-31	PD	2022-11-11	PD	Y
OFFICE-4126	OFFICE-4126	Applied	ancilliary files	E	N	Y				2023-01-31	PD
OFFICE-4132	OFFICE-4132	Applied	3	T	Y	Y	2023-05-01	FC		2023-05-01	FC	2023-04-29	PD	Y
OFFICE-4133	OFFICE-4133	Applied	3	E	Y	N	2023-05-02	FC				2023-04-29	PD	N
OFFICE-4134	OFFICE-4134	Applied	3	E	Y	N	2023-04-24	FC				2023-01-27	PD	N
OFFICE-4137	OFFICE-4137	Applied	3	E	Y	N	2023-04-24	FC				2023-01-27	PD	N
OFFICE-4139	OFFICE-4139	Applied	4	T	Y	N	2023-04-24	FC				2023-01-27	PD	Y
OFFICE-4140	OFFICE-4140	Applied	3	T	Y	Y	2023-04-24	FC		2023-01-31	PD	2023-01-31	PD	Y
OFFICE-4142	OFFICE-4142	Applied		T	N	Y				2023-04-29	PD
OFFICE-4143	OFFICE-4143	Applied	4	T	Y	N	2023-04-26	FC				2023-04-26	FC	Y

	Github #49		3	E	Y	N	2023-05-25	FC				2023-05-30	FC	N