## Sheet1
DEX development
Activities identified in Modellers session in Lillehammer 3-4 March 2005
NOTE. The activities reflect what is proposed performed in a short term range.
The estimated hours are a first draft for the short term tasks.
# | Activity | Main activities [hours] | Sub-activities [hours] | Comments
A1 | DEXlib infrastructure | 276 |  | Support for development of Business Concepts High priority
A2 | Help files | 124
A2.1 | Add definition refined architecture to help/introduction |  | 10
A2.1.1 | Descriptions on exchange contracts |  | 10
A2.1.2 | DEscription of dexs |  | 8
A2.1.3 | DEscription of capabilities |  | 8
A2.1.4 | Description on business concepts |  | 8
A2.2 | Add general usage section |  | 4
A2.2.1 | Explaining use of classification |  | 16
A2.2.2 | Explaining use of idenitifcation |  | 20
A2.2.3 | Explaining use of IGNORE etc as attribute values |  | 20
A2.2.4 | Add a select population matrix |  | 20
A3 | Test data | ???
A3.1 | Define the test data
A4 | Content | 320
A4.1 | Review the core capabilities |  | 240 | High priority
A4.2 | Develop missing core capabilities |  | 10 | High priority
A4.3 | Develop an example business concept for the implementations to use |  | 10 | High priority
A4.4 | Reuse Ref Data from 15926
A4.5 | Review initial baseline of ref data |  | 40
A4.6 | Review |  | 20
A5 | Process | 10
A5.1 | Document process |  | 10
A6 | Reference data | 96
| Harmonize modellers ref data |  | 96 | 4 modellers 3 days workshop
SUM |  | 826