## Slide 1: XLIFF 2.x release cadence
Kevin O’Donnell
JUNE 2014

## Slide 2: Proposal
Yearly cadence for consistency & predictability: publish every May
  Target summer/early fall conferences for promotion & socialization (eg. LocWorld, Unicode)
  Foster cycle of XLIFF development & integration among implementers / tool makers
Open & transparent submission policy
  Standard template for submissions
  Submitters encouraged to own feature specification work
  Statement of use commitment as prerequisite to approval
TC will vote to approve submissions for development
  New XLIFF modules
  Changes to existing XLIFF 2.0 functionality
  Promotion of extension to module
Shortest path through OASIS: single public review
Features not ready / not approved will be postponed
  Statement of use is required prior to final voting
  Keep list of ideas/items for subsequent 2.x release

## Slide 3
Call for submissions
Feature development
Approve OASIS standard
Approve Committee Draft [7 days]
Publish Public Review [30 days]
Reconcile comments, update specification [21 days]
Approve and submit candidate specification [7 days]
Public review of candidate specification [60 days]
Ballot for OASIS Specification approval [14 days]
JUN-SEP
OCT-DEC
JAN-MAY
Survey usage of XLIFF 2.0
Solicit submissions for new modules/changes
Review feedback on existing feature set/implementation
Engage with partner standards committee
Review submissions [October]
Vote on submissions [October]
Feature specification review & approval [November]
Completion of statement of use [November]
Preparation of Committee Draft [December]